## Stakeholder Register
ID | Stakeholder Name | Project Role | Influence | Interest | Needs, Wants & Expectations | Requirements | Concerns | Stakeholder Type | Priority
1 | Sara Schmitt | Project Sponsor | High | High | Financial support, project success, strategic alignment | Funding, project updates, alignment with strategic goals | Project progress, return on investment | Internal | High
2 | Rekha Rani | Senior Stakeholder | High | High | Project success, alignment with organizational goals | Regular updates, strategic alignment | Project direction, organizational impact | Internal | High
3 | Keming Cui | Investors | Medium | High | Return on investment, project success | Financial reports, project milestones | Financial performance, project risks | Internal | High
4 | Shraddha Patle | Suppliers | Low | Low | Project requirements, timely delivery | Compliance with specifications, delivery schedules | Quality of goods/services, reliability | External | Medium
5 | Ashish Bachuwar | Project Manager | High | High | Project completion, adherence to timelines and much more | Project plan, progress reports and much more | Project delays, resource availability and much more | Internal | High
6 | Shriya Kalburge | Third Party Partners | Low | High | Collaboration, mutual success | Coordination, partnership agreements | Partnership conflicts, communication | External | High
7 | Emily Turner | Content Team | High | Low | Creative freedom, project alignment | Content creation schedule, thematic guidelines | Content quality, alignment with brand | Internal | Medium
8 | Rachel Ruby | Regulatory/Compliance Team | Medium | High | Legal compliance, risk mitigation | Regulatory updates, compliance reports | Legal issues, regulatory changes | Internal | Medium
9 | Ankit Bansod | Tech Lead | High | Medium | Technology alignment, project success | Technology stack, development milestones | Technical challenges, project risks | Internal | High
10 | Olivia Martinez | Lead Designer | Medium | Low | User experience, project aesthetics | Design concepts, user feedback | Design inconsistencies, user dissatisfaction | Internal | Medium
11 | Benjamin Turner | Lead Tester | Medium | Low | Bug-free product, quality assurance | Test plans, bug reports | Testing delays, unresolved issues | Internal | Medium
12 | Michael Robinson | Tech/Dev Team | Low | Low | Task completion, adherence to coding standards | Development schedule, coding guidelines | Development delays, coding issues | Internal | Medium
13 | Leopold Fitzroy | Design Team | Low | Low | Aesthetic designs, user-friendly interface | Design concepts, user feedback | Design inconsistencies, user dissatisfaction | Internal | Medium
14 | Penelope Langley | Testing Team | Low | Low | Bug-free product, quality assurance | Test plans, bug reports | Testing delays, unresolved issues | Internal | Medium
15 | Jasper Kingsley | Product Team | High | High | Market success, brand promotion | Marketing plans, target audience | Market competition, brand perception | Internal | High
16 | Edmund Ashcroft | Finance Team | Medium | Medium | Financial stability, budget adherence | Financial reports, budget plans | Budget constraints, financial risks | Internal | Medium
17 | Nathaniel Whitman | Security Team | Low | High | Data protection, risk mitigation | Security protocols, risk assessments | Data breaches, security vulnerabilities | Internal | Medium
Interest
Power/Influence
High Power Low Interest
High Power High Interest
Low Power Low Interest
Low Power High Interest
Project Sponsor
Senior Stakeholder
Investors
Design Team
Tech/Dev Team
Lead Tester
Lead Designer
Tech/Dev lead
Compliance Team
Content Team
3rd Party Partners
Project Manager
Suppliers
Finance Team
Product Team
Testing Team
Security Team

## Stakeholder Comms Plan Matrix
ID | Stakeholder Name | Project Role | Communication Objectives | Communication Method | Frequency | Task(s) Description as per RACI | Feedback Mechanism
1 | Sara Schmitt | Project Sponsor | Funding, project updates, alignment with strategic goals | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Monthly 2) Emails - When required | 1) Consulted throughout the project by various stakeholders. 2) Also accountable upto an extent on whom to approve and establish content licensing/partnership. | Regular project reviews, financial reports
2 | Rekha Rani | Senior Stakeholder | Regular updates, strategic alignment | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual- Bi-Weekly 2) Emails - Frequently as needed | 1) Consulted throughout the project by various stakeholders. 2) Accountable for continuous improvement of the project and some extent on whom to approve and establish content licensing/partnership. | Feedback sessions, alignment check
3 | Keming Cui | Investors | Financial reports, project milestones | Virtual meetings & Emails | 1) Virtual meetings - Monthly 2) Emails - Bi-Weekly | Consulted and informed on various project stages. | Investor meetings, risk discussions
4 | Shraddha Patle | Suppliers | Compliance with specifications, delivery schedules | Virtual meetings & Emails | As needed for both meetings and emails | Informed on the requirements and changes in it. | Quality assessments, delivery feedback
5 | Ashish Bachuwar | Project Manager | Project plan, progress reports and much more | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Depends on the stakeholder type 2) Emails - Regular | Applies all parts of RACI at different stages of the project. | Resource availability, project status
6 | Shriya Kalburge | Third Party Partners | Coordination, partnership agreements | Emails | As needed | Consulted during important stages, otherwise just informed. | Conflict resolution, partnership review
7 | Emily Turner | Content Team | Content creation schedule, thematic guidelines | Virtual meetings & Emails | 1) Virtual meetings - Monthly 2) Emails - When required | Responsible mainly for identifying, negotiating, and establishing content partners. | Content quality evaluation, brand alignment
8 | Rachel Ruby | Regulatory/Compliance Team | Regulatory updates, compliance reports | Virtual meetings & Emails | 1) Virtual meetings - Monthly 2) Emails - When required | Crucial to consult and keep informed at specific stages of the project. | Legal issue resolution, compliance check
9 | Ankit Bansod | Tech Lead | Technology stack, development milestones | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Weekly 2) Emails - Frequently as needed | Accountable during the development and integration stages of the project. | Technical issue resolution, progress check
10 | Olivia Martinez | Lead Designer | Design concepts, user feedback | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Weekly 2) Emails - Frequently as needed | Accountable during the complete design stage of the project. | Design consistency, user satisfaction
11 | Benjamin Turner | Lead Tester | Test plans, bug reports | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Weekly 2) Emails - Frequently as needed | Mainly accountable during different testing techniques and consulted at various other stages. | Testing progress, issue resolution
12 | Michael Robinson | Tech/Dev Team | Development schedule, coding guidelines | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Daily 2) Emails - Regular | Mainly responsible for the development and integration aspects of the project. | Development progress, coding standards
13 | Leopold Fitzroy | Design Team | Design concepts, user feedback | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Daily 2) Emails - Regular | Responsible during the design of the project. | Design quality, user satisfaction
14 | Penelope Langley | Testing Team | Test plans, bug reports | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Daily 2) Emails - Regular | Responsible during the testing phase of the project. | Testing progress, issue resolution
15 | Jasper Kingsley | Product Team | Marketing plans, target audience | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Daily 2) Emails - Regular | This team plays a critical role in being consulted as they manage the backlog and change priorities based on project and stakeholder requirements. | Market feedback, brand perception
16 | Edmund Ashcroft | Finance Team | Financial reports, budget plans | In-Person or Virtual meetings and Emails | 1) In-Person or Virtual - Daily 2) Emails - Regular | Responsible for monetization setup and consulted and informed at important stages of the project to estimate and plan the finances. | Budget constraints, financial risks
17 | Nathaniel Whitman | Security Team | Security protocols, risk assessments | Virtual meetings & Emails | 1) Virtual meetings - Monthly 2) Emails - When required | Responsible for developing security protocols and consulted for security-related phases of the project. | Security assessments, vulnerability checks

## Communication Plan Matrix
Communication Plan Matrix
COMMUNICATION TYPE | PURPOSE | MEDIUM | FREQUENCY | AUDIENCE | OWNER | DELIVERABLES
Kickoff Meeting | 1) Introduce the team and the project. 2) Review objectives and goals. 3) Align stakeholders on goals and expectations. | In-person or Conference call | Once | All Stakeholders | Project Manager & Sponsor | 1) Kickoff agenda & Project overview. 2) Talking to the client through the project stages. 3) Agree on how to work together to successfully deliver the project effectively.
Project Team Meetings/Stand-ups | 1) Create transparency in everyone's daily work/tasks . 2) Coordinate, identify, and resolve any blockers/issues. 3) Facilitate necessary collaboration. | In-person or Conference call & MOM Emails | Daily | Project team and Senior Stakeholders | Project manager | 1) Discuss progress and identify blockers. 2) Ensure everyone is aligned and has visibility over what is going on, good and bad.
Sprint Meetings | 1) Provide clarity and focus on daily scrums. 2) Establish a benchmark for assessing progress, value, and outcomes. 3) Enable efficient and aligned decision-making. | In-person or Conference call & MOM Emails | Bi-Weekly | Product team, Senior Stakeholders and Project manager | Project manager & Scrum Master | 1) Presentation or demonstration of completed work. 2) Document outlining the planned tasks for the upcoming sprint. 3) Updated product backlog with refined user stories and tasks. 4) Summary report indicating whether the sprint goals were achieved.
Technical & Creative Design Meetings | 1) Discuss, and review technical and design problems and solutions. 2) Gather feedback. | In-person or Conference call & Emails | Whenever required | Technical team, Design team, and Project manager | Technical and Design leads + PM | 1) Technical and design documents. 2) Feedback.
Monthly Project Status Meetings | 1) Update leadership on project status. 2) Discuss major milestones. | In-person or Conference call | Monthly | All Stakeholders & Project team | Project manager & project team | 1) Status report. 2) Milestone achievments.
Project Status Reports | Detailed report on project status including progress, costs, and problems. | Email & Drive upload | Monthly | All Stakeholders & Project team | Project manager | 1) Detailed project status. 2) Risk assessments.