## RACI
Roles Milestones/Tasks | Project Sponsor | Senior Stakeholders | Investors | Suppliers | Project Manager | Third Party Partners | Content Team | Regulatory/Compliance Team | Tech Lead | Lead Designer | Lead Tester | Tech/Dev Team | Design Team | Product Team | Testing Team | Finance Team | Security Team | LEGEND
[18 empty] | R | The person/team who performs the task
Design | [17 empty] | A | The one who is answerable for the task's success or failure
Software Architecture | I | I |  |  | I |  |  |  | C | A | C | R | C | C | C | I | I | C | Subject matter experts or stakeholders who provide input
UI Design | I | I | I |  | C | I | C |  |  | A | C | C | R | C | C | I | I | I | Individuals/teams kept updated about task progress
User Engagement Features | I | I | I |  | C | C | C | I |  | A | C | C | R | C | C | I | I
Analytics Dashboard | I | I | I |  | C |  |  |  | C | A | C | C | R | C | C | I
Monetization Setup | C | C | I |  | I | I | I | I | C | A | I | C | I | I | I | R | I
Development | [17 empty] | Stakeholder Information
Infrastructure | C | C | C | I | C | I |  | C | A | C | I | R | C | C | I | C | C | Project Sponsor | Provides financial support and high-level guidance.
UI Features | I | I |  |  | C | I | I | I | A | C | C | R | C | C | C | C | I | Senior Stakeholders | Individuals with significant influence and interest in the project.
Security Protocols | C | C | I |  | I | I | I | C | A |  |  |  |  | I |  | I | R | Investors | Provide financial resources for the project.
Integration | [17 empty] | Suppliers | Provide necessary goods or services.
User Accounts | I | I |  |  | C |  | I | C | A | I | C | R | I | C | C |  | I | Project Manager | Plans, executes, and closes the project.
Technical | I | I |  |  | C |  |  |  | A | I | C | R | I | I | C |  | I | Third Party Partners | External entities with a vested interest in the project.
Content | I | I |  |  | C | C |  | I | A | I | I | R | I | I | I |  | I | Content Creators | Generate project-related content.
AdPartners | I | I |  |  | C | C |  | C | A | I | I | R | I | I | I |  | I | Regulatory/Compliance Authorities | Ensures project compliance with regulations.
Content Licensing/Partnership | [17 empty] | Tech Lead | Leads technical aspects of the project.
Identify Content Partners | A | A | C |  | I | I | R | [9 empty] | C | Lead Designer | Leads project design for a user-friendly experience. | bar: C; I
Negotiate with Content Partners | A | A | C |  | I | I | R | [9 empty] | C | Lead Tester | Leads testing to ensure project quality. | bar: C; I
Establish Contracts with Partners | A | A | C |  | I | I | R | [8 empty] | I | C | Tech/Dev Team | Executes technical development tasks. | bar: C to I
Rights Management | C | C | C |  | A | I | C | R | I | I | I |  |  | C |  | I | C | Design Team | Creates visual and user experience designs.
Testing | [17 empty] | Testing Team | Conducts testing to identify and resolve issues.
Test Strategy | I | I |  |  | C |  |  | I | I | I | A | I | I | C | R | C | I | Marketing Team | Develops and executes marketing strategies.
Compatibility Test | I | I | I |  | C | I |  |  | I | I | A | I | I | I | R | I |  | Finance Team | Manages project finances.
Performance Test | I | I | I |  | C |  |  |  | I | I | A | I | I | I | R | I |  | Security Team | Focuses on ensuring project security.
Usability Test | I | I | I |  | C | I |  |  | I | I | C | I | A | C | R | I
Bug Fixes |  |  |  |  | I | I | I |  | I: A; I: R; C: C; I: I
Launch | [17 empty] | Rationale for Role Assignment in RACI Chart
Content Migration | C | C | C | I | C | C | I | I | A | I | I | R | I | I | I |  | C | The Tech Lead, Lead Designer, and Lead Tester are part of the leadership team. I added them separately since adding only 1 column as "Leadership' wouldn't be easy to interpret.
Continuous Improvement | C: C; C: A; C: C; C: R; C: C; I: C; I: C | C | I | The "Design Team" is responsible for defining the usability criteria, and the "Testing Team" is responsible for executing the usability tests.
Content Creators' here is any individual who creates content and goes live streaming with their followers.
Only the test results are shared with the Project Sponsor and Senior stakeholders.
The Security Team is responsible for developing the initial policies and terms of the security protocols, followed by the technical aspects performed by the tech/dev team.
Some tasks can have multiple teams/persons accountable based on their importance and collaborative decision-making.
The tech/dev team has a considerable number of responsibilities compared to any other team, since this is more of a technical project involving multiple tech/dev teams.