## Gantt Chart & Dependencies
Category | Tasks | Start Date | Earliest Completion Date | Estimated Duration (In Days) | Float | Total Days with Float | Month-Wise Task Scheduling for 2024 | [11 empty] | Dependency Annotations
[7 empty] | January | February | March | April | May | June | July | August | September | October | November | December
1. Design | 1.1 Software Architecture | Jan-01-24 | Jan-26-24 | 19 | 7 | 26 |  | Software Architecture | [10 empty] | This has a lot of dependencies from UI design to Ad partners….
| 1.2 UI Design | Jan-27-24 | Feb-07-24 | 10 | 2 | 38 |  | UI Design | [10 empty] | Relates to the software architecture to help implement the design.
| 1.3 User Engagement Features | Feb-08-24 | Feb-14-24 | 5 | 2 | 45 |  |  | User Engagement Features | [9 empty] | Depends on the UI design & software architecture.
| 1.4 Analytics Dashboard | Feb-15-24 | Feb-27-24 | 11 | 2 | 58 |  |  | Analytics Dashboard | [9 empty] | Depends on how the software architecture is designed.
| 1.5 Monetization Setup | Feb-28-12 | Mar-12-24 | 11 | 3 | 72 | Monetization Setup | [11 empty] | Depends on the overall design & architecture.
2. Development | 2.1 Infrastructure | Mar-13-24 | Apr-11-24 | 24 | 6 | 102 |  |  |  | Infrastructure | [8 empty] | Depends on software architecture design.
| 2.2 UI Features | Apr-12-24 | Apr-20-24 | 6 | 2 | 110 |  |  |  |  | UI Features | [7 empty] | UI Features depends on the UI design
| 2.3 Security Protocols | Apr-21-24 | May-12-24 | 18 | 4 | 132 |  |  |  |  | Security Protocols | [7 empty] | Once the security protocols are defined, then the rights & region content can be managed.
| 2.4 Community Guidelines & Ethics | May-13-24 | May-31-24 | 17 | 2 | 151 |  | Community Guidelines & Ethics
3. Integration | 3.1 User Accounts | Jun-01-24 | Jun-25-24 | 22 | 3 | 176 |  |  |  |  | User Accounts
| 3.2 Technical | Jun-26-24 | Aug-05-24 | 31 | 10 | 217 |  |  |  |  | Technical | [7 empty] | Technical integration depends on software architecure design & monetization setup.
| 3.3 Content | Aug-06-24 | Sep-08-24 | 28 | 6 | 251 | [6 empty] | Content | [5 empty] | Content curation & delivery directly depends on the partners & rights acquired.
| 3.4 AdPartners | Sep-09-24 | Sep-30-24 | 19 | 3 | 273 | [7 empty] | AdPartners |  |  |  |  | Adpartners has dependency on Monetization setup for revenue & software infrastructure design.
4. Content Licensing/Partnership | 4.1 Identify Content Partners | Oct-01-24 | Oct-25-24 | 20 | 5 | 298 | [8 empty] | Identify Content Partners
| 4.2 Negotiate with Content Partners | Oct-26-24 | Nov-08-24 | 13 | 1 | 312 | [8 empty] | Negotiate with Content Partners |  |  |  | In order to netogiate, we have to first identify the content partners.
| 4.3 Establish Contracts with Partners | Nov-09-24 | Nov-18-24 | 9 | 1 | 322 | [9 empty] | Establish Contracts with Partners |  |  | Establishing contracts is possible only after successful negotiations, hence the dependency.
| 4.4 Rights Management | Nov-19-24 | Nov-26-24 | 6 | 2 | 330 | [9 empty] | Rights Management |  |  | Rights management depends on defining the security protocols & community guidelines.
| 4.5 Country/Region Specific Partners/Rights | Nov-27-24 | Nov-30-24 | 3 | 1 | 334 | [7 empty] | Country/Region Specific Partners/Rights |  |  |  |  | This depends on what partners we contract with, the rights to be managed, community guidelines & security protocols defined.
5. Testing | 5.1 Test Strategy | Dec-01-24 | Dec-04-24 | 3 | 1 | 338 | [10 empty] | Test Strategy |  | Test strategy depends on the infrstructure setup.
| 5.2 Compatibility Test | Dec-05-24 | Dec-07-24 | 3 | 0 | 341 | [9 empty] | Compatibility Test |  |  | Compatibility test is depended on the Test strategy
| 5.3 Performance Test | Dec-08-24 | Dec-10-24 | 3 | 0 | 344 | [9 empty] | Performance Test |  |  | Performance test is depended on the Test strategy
| 5.4 Usability Test | Dec-11-24 | Dec-13-24 | 3 | 0 | 347 | [9 empty] | Usability Test |  |  | Usability test is depended on the Test strategy
| 5.5 Bug Fixes | Dec-14-24 | Dec-15-24 | 2 | 0 | 349 | [9 empty] | Bug Fixes |  |  | Fixing bugs is possible only after a test strategy is planned, executed & tested.
6. Launch | 6.1 Content Migration | Dec-16-24 | Dec-20-24 | 4 | 1 | 354 | [9 empty] | Content Migration |  |  | Content Migration is only possible after integrating the technical & content aspects.
| 6.2 Tracking Metrics | Dec-21-24 | Dec-25-24 | 4 | 1 | 359 | [9 empty] | Tracking Metrics |  |  | Once after the design & technical development, Tracking metrics is possible.
| 6.3 Continuous Improvement | Dec-26-24 | Dec-31-24 | 5 | 1 | 365 | [9 empty] | Continuous Improvement

## Schedule on Work Packages
Category | Tasks | Work Packages/Sub-Tasks | Description | Start Date | Earliest Completion Date | Estimated Duration (In Days) | Float | Total Days with Float | Dependencies
1. Design | 1.1 Software Architecture | 1.1.1 System Architecture Design | Designing the overall architecture of the software system. | Jan-01-24 | Jan-07-24 | 7 | 2 | 9 | N/A
|  | 1.1.2 Infrastructure Sizing & Planning | Determining the required infrastructure and planning for its setup. | Jan-10-24 | Jan-19-24 | 7 | 3 | 10 | 1.1.1 System Architecture Design (Must precede)
|  | 1.1.3 High-Level Software Requirements | Defining the high-level software requirements for the project. | Jan-20-24 | Jan-26-24 | 5 | 2 | 7 | 1.1.1 System Architecture Design (Can run concurrently)
| 1.2 UI Design | 1.2.1 UI Concept Development | Developing conceptual ideas for the user interface. | Jan-27-24 | Jan-29-24 | 3 | 0 | 3 | 1.1.1 System Architecture Design (Can run concurrently)
|  | 1.2.2 UI Prototyping | Creating prototypes for the user interface to visualize its design. | Jan-30-24 | Feb-04-24 | 4 | 2 | 6 | 1.2.1 UI Concept Development (Must precede)
|  | 1.2.3 UI Testing & Validation | Testing and validating the user interface to ensure functionality. | Feb-05-24 | Feb-06-24 | 2 | 0 | 2 | 1.2.2 UI Prototyping (Must precede)
|  | 1.2.4 Final UI Design | Finalizing the design of the user interface. | Feb-07-24 | Feb-07-24 | 1 | 0 | 1 | 1.2.3 UI Testing & Validation (Must precede)
| 1.3 User Engagement Features | 1.3.1 Live Chat | Implementing live chat functionality for user interaction. | Feb-08-24 | Feb-14-24 | 5 | 2 | 7 | 1.1.1 System Architecture Design (Can run concurrently)
|  | 1.3.2 Sharing | Adding sharing features for content distribution. | [5 empty] | 1.3.1 Live Chat (Must precede)
|  | 1.3.3 Donations | Implementing a donation system for users. | [5 empty] | 1.3.2 Sharing (Can run concurrently)
| 1.4 Analytics Dashboard | 1.4.1 Data Collection | Collecting and storing data for generating analytics. | Feb-15-24 | Feb-17-24 | 3 | 0 | 3 | 1.1.1 System Architecture Design (Can run concurrently)
|  | 1.4.2 Dashboard UI Design | Designing the user interface of the analytics dashboard. | Feb-18-24 | Feb-24-24 | 5 | 2 | 7 | 1.4.1 Data Collection (Must precede)
|  | 1.4.3 User Engagement Metrics | Defining metrics to measure user engagement. | Feb-25-24 | Feb-27-24 | 3 | 0 | 3 | 1.4.2 Dashboard UI Design (Must precede)
|  | 1.4.4 Real-time Monitoring | Implementing real-time monitoring of user activity. | [5 empty] | 1.4.3 User Engagement Metrics (Must precede)
| 1.5 Monetization Setup | 1.5.1 Ads Integration | Integrating advertisements for revenue generation. | Feb-28-24 | Mar-02-24 | 3 | 1 | 4 | 1.1.1 System Architecture Design (Can run concurrently)
|  | 1.5.2 Subscription Models | Implementing subscription-based revenue models. | Mar-03-24 | Mar-05-24 | 3 | 0 | 3 | 1.5.1 Ads Integration (Must precede)
|  | 1.5.3 Payment Gateway | Setting up a payment gateway for financial transactions. | Mar-06-24 | Mar-09-24 | 3 | 1 | 4 | 1.5.2 Subscription Models (Can run concurrently)
|  | 1.5.4 Revenue Tracking | Tracking and managing revenue generated by the platform. | Mar-10-24 | Mar-12-24 | 2 | 1 | 3 | 1.5.3 Payment Gateway (Must precede)
2. Development | 2.1 Infrastructure | 2.1.1 Network Infrastructure | Set up the network infrastructure for the project. | Mar-13-24 | Mar-19-24 | 6 | 1 | 7 | N/A
|  | 2.1.2 Data Center Setup | Establish and configure the data center for hosting. | Mar-20-24 | Mar-22-24 | 3 | 0 | 3 | 2.1.1 Network Infrastructure (Must precede)
|  | 2.1.3 Scalability Planning | Plan for system scalability to accommodate growth. | Mar-23-24 | Mar-29-24 | 5 | 2 | 7 | 2.1.2 Data Center Setup (Must precede)
|  | 2.1.4 Software & Hardware Procurement | Procure necessary software and hardware components. | Mar-30-24 | Apr-11-24 | 10 | 3 | 13 | 2.1.3 Scalability Planning (Must precede)
| 2.2 UI Features | 2.2.1 Live Chat | Implement live chat features in the user interface. | Apr-12-24 | Apr-20-24 | 6 | 2 | 8 | 1.2.4 Final UI Design (Can run concurrently)
|  | 2.2.2 Sharing | Enable content sharing, likes, comments, and more. | [5 empty] | 1.3.2 Sharing (Must precede)
|  | 2.2.3 Donations | Incorporate donation functionality into the UI. | [5 empty] | 2.2.2 Sharing (Can run concurrently)
| 2.3 Security Protocols | 2.3.1 Security Policies & Compliance | Define security policies and ensure compliance. | Apr-21-24 | Apr-27-24 | 6 | 1 | 7 | 1.1.3 High-Level Software Requirements (Can run concurrently)
|  | 2.3.2 Incident Response & Recovery | Plan and implement incident response and recovery procedures. | Apr-28-24 | May-03-24 | 5 | 1 | 6 | 2.3.1 Security Policies & Compliance (Can run concurrently)
|  | 2.3.3 Permission/Authorization | Establish permission and authorization mechanisms. | May-04-24 | May-06-24 | 3 | 0 | 3 | 2.3.1 Security Policies & Compliance (Must precede)
|  | 2.3.4 Firewall & Violation Detection | Implement firewalls and detection mechanisms for security. | May-07-24 | May-12-24 | 4 | 2 | 6 | 2.3.2 Incident Response & Recovery (Can run concurrently)
| 2.4 Community Guidelines & Ethics | 2.4.1 Establish Safety Measures | Set safety measures to ensure a secure online community. | May-13-24 | May-20-24 | 7 | 1 | 8 | 2.3.3 Permission/Authorization (Can run concurrently)
|  | 2.4.2 Define Community Guidelines | Define guidelines for user behavior and interaction. | May-21-24 | May-23-24 | 3 | 0 | 3 | 2.4.1 Establish Safety Measures (Must precede)
|  | 2.4.3 Create Ethical Guidelines | Develop ethical guidelines for the community to follow. | May-24-24 | May-28-24 | 4 | 1 | 5 | 2.4.2 Define Community Guidelines (Must precede)
|  | 2.4.4 Reporting Mechanism | Implement a reporting mechanism for users to report issues. | May-29-24 | May-31-24 | 3 | 0 | 3 | 2.4.3 Create Ethical Guidelines (Must precede)
3. Integration | 3.1 User Accounts | 3.1.1 Database Setup | Set up the database system for user accounts. | Jun-01-24 | Jun-10-24 | 8 | 2 | 10 | 2.1.2 Data Center Setup (Can run concurrently)
|  | 3.1.2 SSO | Implement Single Sign-On for user authentication. | Jun-11-24 | Jun-13-24 | 3 | 0 | 3 | 3.1.1 Database Setup (Can run concurrently)
|  | 3.1.3 User Access Control | Control user access and permissions within the system. | Jun-14-24 | Jun-20-24 | 6 | 1 | 7 | 3.1.2 SSO (Must precede)
|  | 3.1.4 Notifications & Alerts | Configure notification and alerting systems for users. | Jun-21-24 | Jun-22-24 | 2 | 0 | 2 | 3.1.3 User Access Control (Can run concurrently)
|  | 3.1.5 Feedback & Support | Provide feedback and support mechanisms for users. | Jun-23-24 | Jun-25-24 | 3 | 0 | 3 | 3.1.4 Notifications & Alerts (Can run concurrently)
| 3.2 Technical | 3.2.1 System Integration | Integrate various system components and modules. | Jun-26-24 | Jul-15-24 | 15 | 5 | 20 | 1.4.4 Real-time Monitoring (Must precede)
|  | 3.2.2 API Integration | Integrate external APIs for enhanced functionality. | Jul-16-24 | Jul-25-24 | 7 | 3 | 10 | 3.2.1 System Integration (Must precede)
|  | 3.2.3 Data Migration | Migrate data from existing systems to the new platform. | Jul-26-24 | Jul-31-24 | 5 | 1 | 6 | 3.2.1 System Integration (Must precede)
|  | 3.2.4 Security | Implement security measures for data and system integrity. | Aug-01-24 | Aug-05-24 | 4 | 1 | 5 | 1.3.4 Donations (Can run concurrently)
| 3.3 Content | 3.3.1 Content Delivery | Manage the delivery of content to users. | Aug-06-24 | Aug-15-24 | 8 | 2 | 10 | 1.2.3 UI Testing & Validation (Can run concurrently)
|  | 3.3.2 Content Curation | Curate and organize content for presentation to users. | Aug-16-24 | Aug-22-24 | 6 | 1 | 7 | 3.3.1 Content Delivery (Can run concurrently)
|  | 3.3.3 Regional Content Integration | Integrate region-specific content for diverse audiences. | Aug-23-24 | Sep-08-24 | 14 | 3 | 17 | 3.3.2 Content Curation (Must precede)
| 3.4 AdPartners | 3.4.1 Integration Planning | Plan the integration of advertising partners. | Sep-09-24 | Sep-20-24 | 10 | 2 | 12 | 1.4.3 User Engagement Metrics (Can run concurrently)
|  | 3.4.2 Technial Integration | Integrate technical aspects of advertising partners. | Sep-21-24 | Sep-30-24 | 9 | 1 | 10 | 3.4.1 Integration Planning (Must precede)
4. ContentLicensing/Partnership | 4.1 Identify Content Partners | 4.1.1 Market Research | Research the market to identify potential content partners. | Oct-01-24 | Oct-07-24 | 5 | 2 | 7 | N/A
|  | 4.1.2 Industry Analysis | Analyze the industry to select suitable content partners. | Oct-08-24 | Oct-13-24 | 5 | 1 | 6 | 4.1.1 Market Research (Can run concurrently)
|  | 4.1.3 Partner Identification | Identify and shortlist content partners for collaboration. | Oct-14-24 | Oct-25-24 | 10 | 2 | 12 | 4.1.2 Industry Analysis (Must precede)
| 4.2 Negotiate with Content Partners | 4.2.1 Contract Negotiation | Negotiate contracts with the partners | Oct-26-24 | Oct-31-24 | 6 | 0 | 6
|  | 4.2.2 Licensing Terms & Agreements | Define licensing terms and agreements with content partners. | Nov-01-24 | Nov-05-24 | 4 | 1 | 5 | 4.1.3 Partner Identification (Must precede)
|  | 4.2.3 Legal Review | Conduct legal reviews to ensure the legality and compliance of agreements. | Nov-06-24 | Nov-08-24 | 3 | 0 | 3 | 4.2.2 Licensing Terms & Agreements (Must precede)
| 4.3 Establish Contracts with Partners | 4.3.1 Agreement Execution | Execute and finalize contracts with content partners. | Nov-09-24 | Nov-14-24 | 5 | 1 | 6 | 4.2.3 Legal Review (Can run concurrently)
|  | 4.3.2 Content Delivery Terms | Establish terms for content delivery and distribution. | Nov-15-24 | Nov-16-24 | 2 | 0 | 2 | 4.3.1 Agreement Execution (Must precede)
|  | 4.3.3 Content Scheduling | Plan the schedule for content release and updates. | Nov-17-24 | Nov-18-24 | 2 | 0 | 2 | 4.3.2 Content Delivery Terms (Can run concurrently)
| 4.4 Rights Management | 4.4.1 Content Rights Acquisition | Acquire and manage rights for the content to be used. | Nov-19-24 | Nov-22-24 | 3 | 1 | 4 | 4.2.2 Licensing Terms & Agreements (Must precede)
|  | 4.4.2 Rights Tracking & Expiry Management | Track and manage content rights, including expiry dates. | Nov-23-24 | Nov-23-24 | 1 | 0 | 1 | 4.4.1 Content Rights Acquisition (Can run concurrently)
|  | 4.4.3 Compliance & Reporting | Ensure compliance with content usage agreements and report on it. | Nov-24-24 | Nov-26-24 | 2 | 1 | 3 | 4.4.2 Rights Tracking & Expiry Management (Must precede)
| 4.5 Country/Region Specific Partners/Rights | 4.5.1 North America | Focus on content partnerships and rights specific to North America. | Nov-27-24 | Nov-30-24 | 3 | 1 | 4 | 4.2.3 Legal Review (Can run concurrently)
|  | 4.5.2 Asia | Focus on content partnerships and rights specific to the Asian region. | [5 empty] | 4.5.1 North America (Can run concurrently)
|  | 4.5.3 Europe | Focus on content partnerships and rights specific to Europe. | [5 empty] | 4.5.2 Asia (Can run concurrently)
5. Testing | 5.1 Test Strategy | 5.1.1 Test Plan Development | Develop a comprehensive plan for testing activities. | Dec-01-24 | Dec-04-24 | 3 | 1 | 4 | 1.4.4 Real-time Monitoring (Can run concurrently)
|  | 5.1.2 Test Environment Setup | Configure the testing environment with necessary tools and resources. | [5 empty] | 5.1.1 Test Plan Development (Must precede)
|  | 5.1.3 Test Case Design | Create test cases and scenarios for thorough testing. | [5 empty] | 5.1.2 Test Environment Setup (Must precede)
|  | 5.1.4 Test Execution | Execute the planned tests and record results. | [5 empty] | 5.1.3 Test Case Design (Must precede)
| 5.2 Compatibility Test | 5.2.1 Test Plan | Create a test plan specifically for compatibility testing. | Dec-05-24 | Dec-07-24 | 3 | 0 | 3 | 5.1.4 Test Execution (Must precede)
|  | 5.2.2 Cross-Browser Testing | Test the application's compatibility with various web browsers. | [5 empty] | 5.2.1 Test Plan (Must precede)
|  | 5.2.3 Cross-Device Testing | Test the application's compatibility with different devices. | [5 empty] | 5.2.2 Cross-Browser Testing (Can run concurrently)
|  | 5.2.4 Test Report | Generate a report summarizing compatibility test results. | [5 empty] | 5.2.3 Cross-Device Testing (Must precede)
| 5.3 Performance Test | 5.3.1 Test Plan | Develop a test plan for assessing system performance. | Dec-08-24 | Dec-10-24 | 3 | 0 | 3 | 5.1.4 Test Execution (Can run concurrently)
|  | 5.3.2 Load Testing | Evaluate system performance under various load conditions. | [5 empty] | 5.3.1 Test Plan (Must precede)
|  | 5.3.3 Stress Testing | Subject the system to stress testing to assess its limits. | [5 empty] | 5.3.2 Load Testing (Can run concurrently)
|  | 5.3.4 Performance Metrics | Measure and record performance metrics for analysis. | [5 empty] | 5.3.3 Stress Testing (Must precede)
| 5.4 Usability Test | 5.4.1 Test Plan | Create a test plan for assessing the usability of the UI. | Dec-11-24 | Dec-13-24 | 3 | 0 | 3 | 5.1.4 Test Execution (Can run concurrently)
|  | 5.4.2 UI Testing | Conduct tests to evaluate the usability of the user interface. | [5 empty] | 5.4.1 Test Plan (Must precede)
|  | 5.4.3 User Experience Assessment | Assess the overall user experience and gather feedback. | [5 empty] | 5.4.2 UI Testing (Can run concurrently)
|  | 5.4.4 Usability Feedback | Collect feedback from users to improve usability. | [5 empty] | 5.4.3 User Experience Assessment (Must precede)
| 5.5 Bug Fixes | 5.5.1 Bug Identification | Identify and document software bugs and issues. | Dec-14-24 | Dec-15-24 | 2 | 0 | 2 | 5.4.4 Usability Feedback (Can run concurrently)
|  | 5.5.2 Bug Resolution | Resolve identified bugs and issues in the software. | [5 empty] | 5.5.1 Bug Identification (Must precede)
|  | 5.5.3 Quality Assurance | Ensure the overall quality and reliability of the software. | [5 empty] | 5.5.2 Bug Resolution (Can run concurrently)
|  | 5.5.4 Documentation | Update and maintain documentation related to the software. | [5 empty] | 5.5.3 Quality Assurance (Must precede)
|  | 5.5.6 User Feedback Implementation | Implement improvements based on user feedback and suggestions. | [5 empty] | 5.5.4 Documentation (Can run concurrently)
6. Launch | 6.1 Content Migration | 6.1.1 Migration Plan | Plan the migration of content from the old system to the new one. | Dec-16-24 | Dec-20-24 | 4 | 1 | 5 | 2.2.4 Donations (Can run concurrently)
|  | 6.1.2 Data Transfer & Verification | Transfer data and verify its accuracy during migration. | [5 empty] | 6.1.1 Migration Plan (Must precede)
|  | 6.1.3 Content Validation & Catalog Updates | Validate migrated content and update the catalog accordingly. | [5 empty] | 6.1.2 Data Transfer & Verification (Must precede)
|  | 6.1.4 Rollout Planning | Plan the rollout of the new system and its features. | [5 empty] | 6.1.3 Content Validation & Catalog Updates (Must precede)
| 6.2 Tracking Metrics | 6.2.1 Defining KPIs | Define Key Performance Indicators (KPIs) to track system performance. | Dec-21-24 | Dec-25-24 | 4 | 1 | 5 | 2.4.3 Create Ethical Guidelines (Can run concurrently)
|  | 6.2.2 Data Collection Mechanisms | Establish mechanisms for collecting data related to KPIs. | [5 empty] | 6.2.1 Defining KPIs (Must precede)
|  | 6.2.3 Real-time Dashboard | Create a real-time dashboard for monitoring KPIs. | [5 empty] | 6.2.2 Data Collection Mechanisms (Must precede)
|  | 6.2.4 Monthly Reports | Generate monthly reports based on KPI data and analysis. | [5 empty] | 6.2.3 Real-time Dashboard (Must precede)
| 6.3 Continuous Improvement | 6.3.1 User Feedback Analysis | Analyze user feedback and identify areas for improvement. | Dec-26-24 | Dec-31-24 | 5 | 1 | 6 | 5.5.6 User Feedback Implementation (Can run concurrently)
|  | 6.3.2 Probelm Resolution | Resolve problems and issues identified through feedback. | [5 empty] | 6.3.1 User Feedback Analysis (Can run concurrently)
|  | 6.3.3 Feature Prioritization | Prioritize features and enhancements based on user feedback. | [5 empty] | 6.3.2 Problem Resolution (Must precede)
|  | 6.3.4 Collaborating with more Partners | Explore collaborations with additional content or service partners. | [5 empty] | 6.3.3 Feature Prioritization (Can run concurrently)
|  | 6.3.5 User Engagement Initiative | Develop initiatives to enhance user engagement on the platform. | [5 empty] | 6.3.4 Collaborating with more Partners (Can run concurrently)
Total | [7 empty] | 365

## Critical Path
0
A
56
0
0
0
56
56
A. Design B. Development C. Integration D. Content Licensing/Partnership E. Testing F. Launch
LEGEND
Critical Path for Netflix Live-Streaming Project
56
B
121
0
0
56
65
121
121
C
221
0
0
121
100
221
121
D
172
49
49
170
51
221
221
E
235
0
0
221
14
235
235
F
248
0
0
235
13
248
Early Start
ID
Early Finish
Slack
Slack
Latest Start
Duration
Latest Finish
221
172
Critical Path
Critical Path
Critical Path
Critical Path