## Budget Estimate
LEGEND
[8 empty] | Target | Cost forecasted for the task to incurr.
[8 empty] | Actual | Actual cost incurred for the task. Right now, its empty since the project is expected to start on Jan-01-24.
[8 empty] | Variance | The difference amount for cost estimated Vs Actual cost incurred.
Category/Milestone | Task | Labor |  | Material |  | Target (In millions) | Actual (In Millions) | Variance (In Millions) | Description for Target Cost Estimate
|  | Hours | Rate/Hour | Units | $/Unit
1. Design | 1.1 Software Architecture | 410000 | 90 | 50 | 62000 | 40000000 |  | 40000000 | This amount is allocated to the teams of experienced software architects to design a robust system, along with software tools or licenses required for architecture design.
| 1.2 UI Design | 400000 | 80 | 600 | 30000 | 50000000 |  | 50000000 | This budget accounts for hiring skilled UI designers, software licenses, and design assets, graphic design software or stock images are required.
| 1.3 User Engagement Features | 375000 | 90 | 125 | 50000 | 40000000 |  | 40000000 | Developing engaging features to keep users interested requires skilled programmers, and designers, and utilizing external software libraries or tools/resources.
| 1.4 Analytics Dashboard | 250000 | 80 | 0 | 0 | 20000000 |  | 20000000 | Building an advanced analytics dashboard is crucial for monitoring user behavior and platform performance, which involves data experts and software development and specialized data analytics software or external data sources are required.
| 1.5 Monetization Setup | 150000 | 100 | 10 | 500000 | 20000000 |  | 20000000 | Establishing monetization features, including payment processing, requires developers, legal consultants, and financial experts and utilizing payment gateway services or financial software licenses are needed.
| Total cost estimate for Design |  |  |  |  | 170000000
2. Development | 2.1 Infrastructure | 500000 | 80 | 5000 | 8000 | 80000000 |  | 80000000 | Building a robust infrastructure is essential, involving IT experts, hardware investments, and cloud service subscriptions including purchasing hardware, servers, network equipment, and security software.
| 2.2 UI Features | 575000 | 90 | 10 | 700000 | 58750000 |  | 58750000 | Implementing additional UI features requires front-end developers and design resources to enhance user experience and external software tools or assets may be required for implementing specific features.
| 2.3 Security Protocols | 190000 | 80 | 550 | 29000 | 31150000 |  | 31150000 | Ensuring platform security is a priority, necessitating cybersecurity experts, software tools, encryption technologies and purchasing security software, licenses, and hardware security modules.
| 2.4 Community Guidelines & Ethics | 400000 | 100 | 0 | 0 | 40000000 |  | 40000000 | Developing and enforcing community guidelines and ethical standards involves legal consultants, content experts, and ongoing moderation, legal consulting services or training materials maybe needed.
| Total cost estimate for Development |  |  |  |  | 209900000
3. Integration | 3.1 User Accounts | 350000 | 100 | 60 | 80000 | 39800000 |  | 39800000 | Implementing user accounts requires developers and database management to ensure user data is handled securely and specialized user account management software maybe required.
| 3.2 Technical | 400000 | 120 | 40 | 60000 | 50400000 |  | 50400000 | Technical integration involves IT experts, data migration tools, and resources for data synchronization and software development tools, licenses, and testing equipment purchasing.
| 3.3 Content | 400000 | 120 | 30 | 55000 | 49650000 |  | 49650000 | Integrating content from various sources involves content managers and data synchronization tools and specific content creation software or licenses maybe required.
| 3.4 AdPartners | 400000 | 100 | 0 | 0 | 40000000 |  | 40000000 | Collaborating with advertising partners requires negotiations, legal consultations, partnership agreements, and legal consulting services or partner-related expenses maybe involved.
| Total cost estimate for Integration |  |  |  |  | 179850000
4. Content Licensing/Partnership | 4.1 Identify Content Partners | 350000 | 80 | 20 | 500000 | 38000000 |  | 38000000 | Identifying suitable content partners involves market research, partnership scouting, and material costs may apply if market research reports or partner databases are purchased.
| 4.2 Negotiate with Content Partners | 300000 | 82 | 500 | 10000 | 29600000 |  | 29600000 | Negotiations with content partners require legal experts and business development professionals. Material costs may apply if legal consulting services or travel expenses are involved in negotiations.
| 4.3 Establish Contracts with Partners | 350000 | 80 | 20 | 70000 | 29400000 |  | 29400000 | Establishing contracts with partners involves legal consultants and the costs of formalizing partnership agreements. Material cost may apply if legal services for contract drafting are hired or document management software is used.
| 4.4 Rights Management | 30000 | 80 | 23 | 30000 | 3090000 |  | 3090000 | Managing content rights requires rights experts and legal consultants along with materials for rights management software, licenses, or legal services.
| 4.5 Country/Region Specific Partners/Rights | 250000 | 80 |  |  | 20000000 |  | 20000000 | Expanding into specific regions necessitates market analysis and legal consultations.
| Total cost estimate for Content Licensing/Partnership |  |  |  |  | 120090000
5. Testing | 5.1 Test Strategy | 420000 | 70 | 15 | 30000 | 29850000 |  | 29850000 | Developing a comprehensive test strategy requires testing experts, testing tools, and planning resources. Also, material cost maybe applied if specialized testing tools or software are needed.
| 5.2 Compatibility Test | 250000 | 80 |  |  | 20000000 |  | 20000000 | Testing compatibility involves testers and test devices, requiring equipment and personnel.
| 5.3 Performance Test | 350000 | 70 | 150 | 36000 | 29900000 |  | 29900000 | Performance testing necessitates testing experts and load-testing tools to ensure platform stability. Material cost for performance testing tools, licenses, and necessary hardware maybe applied.
| 5.4 Usability Test | 375000 | 80 | 0 | 0 | 30000000 |  | 30000000 | Usability testing involves usability experts and compensation for test participants.
| 5.5 Bug Fixes | 100000 | 80 | 30 | 50000 | 9500000 |  | 9500000 | Addressing bugs and issues identified during testing requires developers and quality assurance professionals. Materials may be applied for bug tracking software, licenses, and testing environments.
| Total cost estimate for Testing |  |  |  |  | 119250000
6. Launch | 6.1 Content Migration | 350000 | 70 | 70 | 80000 | 30100000 |  | 30100000 | Migrating content involves data experts and content migration tools to ensure a seamless transition.
| 6.2 Tracking Metrics | 120000 | 80 | 0 | 0 | 9600000 |  | 9600000 | Tracking platform metrics and user behavior requires data analysts and analytics tools for data-driven decision-making.
| 6.3 Continuous Improvement | 450000 | 82 | 10 | 40334 | 37303340 |  | 37303340 | Ongoing improvements involve data experts and development resources to enhance the platform over time.
| Total cost estimate for Launch |  |  |  |  | 77003340
| Contingency (10%) |  |  |  |  | 123906680 |  | 123906680 | The contingency budget of 10% is included to address unforeseen expenses and ensure the project stays within budget while accounting for unexpected challenges.
Total Cost Estimate for the Project | [5 empty] | 1000000020 |  | 1000000020

## Budget Control Plan
Frequency of Budget Revisit
Monthly Budget Revisits |  | In the initial stages of the project, budget will be revisited on a monthly basis. This frequency will allow us for close monitoring of project expenditures and cost performance throughout the stages. It helps us to identify potential issues early on and enables prompt corrective actions.
Quarterly Budget Revisits |  | As the project progresses and we reach the major milestones, we will switch to a quarterly budget review schedule. This frequency provides a balance between close monitoring and the need for strategic assessments.
On-demand or Triggered Budget Revisits |  | The project team will also be prepared for on-demand or triggered budget revisits. These revisits can be called for in response to significant project events, such as unexpected market developments, and changes in scope i.e., Scope Creep or financial emergencies. In such cases, a budget revisit will occur immediately.
Metrics to Monitor Cost & Time Estimates
S.No | Cost Estimation Metrics | Description | Frequency
1 | Cost Performance Index (CPI) | CPI measures the efficiency of cost spending. It is calculated as the ratio of the earned value (the value of work actually performed) to the actual cost. A CPI greater than 1 indicates cost efficiency, while less than 1 indicates overspending. | CPI will be calculated and reported regularly, such as weekly or monthly, depending on the project's duration and complexity.
2 | Cost Variance (CV) | CV is the difference between the earned value and the actual cost, indicating whether the project is over or under budget. | CV will be calculated and reported regularly, like CPI.
3 | Budget At Completion (BAC) | BAC represents the total budgeted cost for the entire project, providing a reference point for comparing actual costs. | BAC can be reported at the beginning of the project and reviewed periodically i.e., with every milestone achieved.
4 | Cost Baseline | The cost baseline is the approved budget for the project, which serves as a reference for comparing actual costs. | Cost baseline will be established at the beginning of the project and to be reviewed as necessary, especially when there are significant budget changes.
S.No | Time Estimation Metrics | Description | Frequency
1 | Schedule Performance Index (SPI) | SPI measures the efficiency of time scheduling by comparing the earned value to the planned value. An SPI greater than 1 indicates ahead-of-schedule progress, while less than 1 indicates delays. | SPI will be calculated and reported regularly, similar to CPI.
2 | Schedule Variance (SV) | SV represents the difference between the earned value and the planned value, indicating whether the project is ahead of or behind schedule. | SV will be calculated and reported regularly on a monthly basis.
3 | Planned Value (PV) | PV is the planned or budgeted value of work scheduled to be completed during a specific period, providing a reference for comparing actual progress. | PV is calculated and reported regularly as part of schedule monitoring.
4 | Project Schedule | The project schedule, which includes milestones and critical path analysis, is a key document for tracking project timelines. | The project schedule will be reviewed and updated as needed, which may be weekly or monthly depending on how complex the project gets with each phase.